## Revised Plan
Revised w. Sif fixed Monday
| 48 |  |  |  | Sif booked from 24.11 - 28.11
2025-11-24 |  | Sif Service |  |  | Odin is not, run on Odin?
2025-11-25 | Tues. | Ramp, 105-600C, 10% O2 |  | Sif
2025-11-26 | Wed. | 200, 10% O2 | No PW | Sif
2025-11-27 | Thurs. | 225, 10% O2 |  | Sif
2025-11-28 | Fri. | 250, 10% O2 |  | Sif
49
2025-12-01 |  | BET + 275, 10% O2 | 275 for PW | Sif |  | Ramp, 105-600C, 10% O2 |  | Sif
2025-12-02 |  | BET + Ramp 105-600C, 5% O2 |  | Sif |  | 200, 10% O2 | No PW | Sif
2025-12-03 |  | 200, 5% O2 | no PW | Sif |  | 225, 10% O2 |  | Sif
2025-12-04 |  | 225, 5% O2 |  | Sif |  | 250, 10% O2 |  | Sif
2025-12-05 |  | 250, 5% O2 |  | Sif |  | BET + 275, 10% O2 | 275 for PW | Sif
50
2025-12-08 |  | BET + Ramp 105-600C, 5% O2 |  | Sif
2025-12-09 |  | 200, 5% O2 | no PW | Sif
2025-12-10 |  | 225, 5% O2 |  | Sif
2025-12-11 |  | 250, 5% O2 |  | Sif
2025-12-12 |  | 275, 5% O2 | for PW | Sif

## Revised Sif broken
| 48 | test | Done? | Note(s) | TG
2025-11-24 |  | Ramp, 105-600C, 10% O2 |  |  | Odin
2025-11-25 | Tues. | 200, 10% O2 |  | No PW | Odin | Assumes 1 single test per biohar 4H hold
2025-11-26 | Wed. | 225, 10% O2 |  |  | Odin | Assumes 1 single test per biohar 4H hold
2025-11-27 | Thurs. | 275, 10% O2 |  | for PW | Odin | Assumes 1 single test per biohar 4H hold | Priority:
2025-11-28 | Fri. | 250, 10% O2 |  |  | Odin | 1 test per, 10H hold | 1. Ramps | Done
| 49 | [5 empty] | 2. 225 + 250C
2025-12-01 |  | BET + 200, 5% O2 |  | no PW | Sif | Assumes 1 single test per biohar 4H hold | 3. 200C
2025-12-02 |  | BET + 225, 5% O2 |  |  | Sif | Assumes 1 single test per biohar 4H hold | 4. 275C
2025-12-03 |  | 105 - 600C 5% O2 |  |  | Sif | Assumes 1 single test per biohar 4H hold | 5. re-runs | BRF500 ramp 5%
2025-12-04 |  | 275, 5% O2 |  |  | Sif | Assumes 1 single test per biohar 4H hold
2025-12-05 |  | 250, 5% O2 |  |  | Sif | 10H hold
50
2025-12-08 |  | If possible: 20% O2, 200C |  |  | Sif

## Original Plan
Week Number | Experiments | Done? | Notes | TGA used/planne
45 | 225, 20% O2 | ✅ | Single run, 4H hold | Sif
| 200, 5% O2 | X | Single run, 4H hold | Sif
| 225, 5% O2 | X | Single run, 6H hold | Sif
| CHNS | ✅ |  | Analytical Hub
| VM Feedstock | ✅ |  | Sif
46 |  |  |  |  | Changes:
| 250, 5% O2 | X | 10H Hold normal | Sif | Sif broke, had to do Odin <-> Sif checks
| 105-800, 5% O2 | X |  | Sif
| 200, 10% O2 | X |  | Sif
| 250 10% O2 | X |  | Sif
| VM Biochar | ✅ |  | Odin
47
| 225, 10% O2 | X |  | Sif
| 105-800 10% O2 | X |  | Sif